## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
DT | 102469 | Portable | Portable Relocation # 39 DM from San Miguel | Completed - New wood for ramps and 1 Heater
CHS | 108957 | Sidewalks | Demo and replace concrete to (2) sections of sidewalks and a 10x20 | Complete
| 108963 |  | slab of concrete for Ground Morgan Bldg.
CHS | 105901 | Gym Floor | Repair (3) entrances to gym, where floor is buckling | 2013-12-01
GHS | 109343 | Baseball Field | 6' Fence around boys baseball batting cages | 2014-03-01
GHS | 110768 | Baseball Field | Install new batting cages | 2014-03-01
GMS | 108222 | Front Campus | Remove mulberry trees from planters and prep for planting. | Removal of trees & planting by others - Complete
Working on providing water source and electrical
for irrigation system.
GMS | 110835 | Permit | Acquire "Right of Use Permit" for 40ft of left bank of Anthony Drain | Permit Approved by EBID on 11/22/13
|  |  | for parking access, fence and landscaping. | Filing of Drain by EBID to begin w/GISD pays
for materials (piping).
MQ | 79890 | Playing Fields | Provide water for irrigation of playing fields. | Started on project - Pending Summer
Need to install new irrigation system.
MQ |  | Nurses Office | Install additional double doors in office. | 75 % Complete (Painting & Electrical - Pending)
Northern Pre-K | 108567 | Sidewalks | Remove and pour new ADA sidewalks | 2013-12-01
108568
STMS | 109828 | Gym | Repair of floor buckling by locker rooms | Complete
District Wide | 104223 | Pre-K Centers | Build raised planters at sites. | 104223- CHS Pre-K Complete 11/27/13
AE, CHS
LM