## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
CMS |  | PE Locker Replacement |  | 2014-07-01
CH-Pre-K |  | Playground | Replace sand with Engineered Wood Fiber | Spring Break April 7-11, 2014
Fall Area
CHS | 93777 | Soccer Field | Install canopy shades | 2014-08-01
GAC |  | IT Office | Asbestos Abatement | 2014-06-01
GHS | 109343 | Baseball Field | 6' Fence around boys baseball batting cages | Complete
GHS | 110437 | Baseball Field | Install new batting cages | Complete
GMS | 108222 | Front Campus | Remove mulberry trees from planters and prep for planting. | Removal of trees & planting by others - Complete
Working on providing water source and electrical
for irrigation system.
GMS | 110835 | Permit | Acquire "Right of Use Permit" for 40ft of left bank of Anthony Drain | Permit Approved by EBID on 11/22/13
|  |  | for parking access, fence and landscaping. | Filing of Drain by EBID - Complete
Fence Pending
GMS |  | C-Wing | Asbestos Abatement | 2014-06-01
MQ | 95182 | Playing Fields | Provide water for irrigation of playing fields. | Complete
Need to install new irrigation system.
MQ |  | Nurses Office | Install additional double doors in office. | 90% Complete on installing closers
Pending Electrical
MQ | 111219 | Septic Tank | Demolish and remove abandoned septic tank and pumps. | 2014-04-01
STE | 112234 | Bus Turnaround | Metal canopy shades for students | 2014-08-01
STMS | 112136 | Fire Hydrants | Replacement of (5) Fire Hydrants | Tentative during Spring Break