## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
CH-Prek | 166818 | Parking Lot | Install bollards to stop through traffic to CHS. | Completed 1/18/17
CHS | 158572 | Bleachers | Anchor small bleachers with ties. | Completed 1/12/17
GMS | 158569 | Bleachers | Anchor small bleachers with ties. | Completed 1/31/17
STHS | 158574 | Bleachers | Anchor small bleachers with ties. | Completed 2/9/17
GMS/C-Wing | 163897 | Nurses Portable | Need to replace roof. | Completed 2/7/17
DV | 166799 | Main Water | Repair backflow | Completed 2/7/17
GHS | 158573 | Bleachers | Anchor small bleachers with ties. | 2017-03-30
GMS | 163706 | Gym | Need to replace basketball goal. | 2017-03-30
GMS | 162696 | Gym | Need to repair bleachers. | 2017-03-30
NV | 169416 | Drainage | Improve drainage behind school. | 2017-03-30
NV | 169104 | Concrete | Install concrete for ADA access to playgrounds. | 2017-03-30
SR | 170982 | Grounds | Upgrade irrigation system to increase water pressure for additional | 2017-03-30
gardening beds being installed by La Semilla
STMS | 158575 | Bleachers | Anchor small bleachers with ties. | 2017-03-30
STMS | 170980 | Library | Replace light fixtures w/LED Lamps (safety issue) | 2017-04-15
BE | 170981 | Grounds | Install irrigation system for (14) fruit trees that will be planted by | 2017-04-15
La Semilla.
GAC | 170630 | Parking | Install LED Lamps on in fixtures. | 2017-04-30
CHS | 160842 | Fields | Repair broken concrete. | 2017-04-30
BE/CH/CM/NV | 168704 | Fire Suppression | Repair of Fire Suppression Systems. | 2017-04-30
168776
168780
170163
GAC | 170964 | Server Room | Upgrade A/C system. | 2017-05-30
YH | 167094 | Playground | Install curbs to contain wood-chips | 2017-05-30
STHS | 170979 | Football/Track Field | Annual Maintenance and Repair of fields. | 2017-06-30
CHS | 170978 | Football/Track Field | Annual Maintenance and Repair of fields. | 2017-06-30
GHS | 170976 | Track | Annual Maintenance of Track. | 2017-06-30
GHS | 170975 | Football Field Turf | Replace artificial turf. | 2017-07-15
YH | 167093 | North Wing | Install portable building | 2017-07-30

## 16-17
LU | 154214 | Entrance | Install new marquee. | Complete
SPE | 148041 | Entrance | Establish more secure entrance. | Complete
VE | 151368 | Dumpsters | Construct trash area w/wall | Complete
VE | 149482 | Playground | Create drainage system in play area | Complete
STHS | 152246 | Baseball Field | Install Backstops | Complete
CHS | 154707 | Buildings and Fields | Repair Geothermal Lines | Complete
STHS | 144169 | Locker Room | Re-build wall and Re-tile to due to water damage. | Complete
STHS | 155417 | Science Room | Install science table countertops. | Completed 10/4/16
LU | 158411 | Marquee | Run 220v 20amp power to marquee. | Completed 10/11/16
STHS | 153170 | Softball Field | Install Backstops | Completed 10/4/16
GHS | 152152 | Baseball Field | Install Backstops | Completed 10/11/16
GHS | 153169 | Softball Field | Install Backstops | Completed 10/11/16
SR | 154093 | Lift Station | Repair lift station | Completed 10/5/16
MQ | 151615 | Roof | Repair metal roof and soffits. | Completed 10/4/16
GMS | 161480 | Gym | CD Mechanical to perform intrusive exploration of sewer to locate | Completed 10/11/16
origin of sewage smell.
SPE | 159803 | Playground | Repair of several sidewalks. | Completed 10/24/16
CMS | 158570 | Bleachers | Construct concrete slab and anchor small bleachers. | Completed 11/28/16
CMS | 158571 | Bleachers | Construct concrete slab and anchor large bleachers. | Completed 11/28/16
GHS | 163894 | Fire Pump | Need to repair leak on packing's. | Completed 11/29/16
LU | 163664 | Front Area | Need to remove old marquee. | Completed 11/19/2016
SM | 165024 |  | Remove water supply. | Completed 12/5/16

## 15-16
STHS | 124792 | Football Field | New Scoreboard | Complete 7/14/15
STHS | 130086 | Main Parking Lot | Replace chain link roll gates w/wrought iron gates. | 8/31/2015 - As per Mr. Holguin this project will
|  | Entry Gates |  | be completed by Contactor.
LM - Pre-K | 113535 | Playground | Remove sand and fill in with wood chips and build curbs around | Complete
playground.
DT |  | Portables | Move in (3) double portables. | Complete
Alta Vista ECHS |  | C-Wing | Remodeling - Change signs, Windows, Asbestos Abatement-New Flooring | Complete 8/19/15
GHS | 134308 | Field Restroom | Re-roof, paint and install signage | Complete
STHS | 131378 | Nurses Portable | Remodeling Clinical De Familia side for School Nurses, installation of | Complete
new restroom.
NV | 132916 | Playground | Install new shade canopies over playground. | Complete
LL | 137754 | Parking Lot | Repaint Parking lot including Handicap parking areas and fire lanes | Complete
STHS | 132919 | Auxiliary Gym | Replace scoreboard with new one. | Complete
Install scoreboard.
GMS - C-Wing | 141678 | Sewer | Repair of sewer system. | Complete
AVECHS
LL | 136411 | Playground | Install wood chips in place of sand in playground. Replace plastic | Complete
curbs with cement and new ADA access.
GE | 137710 | Parking Lot | Repaint Parking lot | Complete
STHS | 139217 | Sewer | Major sewer line replacement in building (3 phases) | Complete
STHS | 128389 | Tennis Courts | Re-condition playing surface | Complete
STHS | 132037 | Parking Lot Entrance | New wrought-iron gate to entrance of parking lot. | Complete
PPD | 129148 | Shops | Install upgraded electrical service for shop area. | Complete
RS | 132046 | Marquee | Install new LED Marquee | Complete
STE | 140025 | Playground | Wood chips and concrete curbs | Complete
STHS | 131970 | Football Field | New visitors bleachers to conform to code. | Complete
PPD | 141679 | Maint Warehouse | Move maintenance distribution from old warehouse to new. | Complete
CHS | 141677 | Geothermal Lines | Repair of lines throughout building. | Complete
LU | 143295 | Mechanical Room | Replace old damaged water heater w/boiler system for domestic. | Complete
CHS | 141351 | Football Field | Install ADA accessible sidewalk at visitors side. | Complete
LL | 141373 | Classrooms | Install new VCT floor in 7 classrooms. | Complete
STHS | 139966 | Marquee | Install new LED Marquee | Complete
STHS | 127644 | Softball Field | Batting cages for softball field please see Ms Contreras or Rick | Complete
NV | 122505 | Bus Turnaround | Build shade canopy on East Side | Complete
LU | 140718 | Playground | Wood chips and concrete curbs | Complete
CMS | 143314 | Parking | Create location for trash bins at Bus Turn-around | Complete
RTC | 143605 | Portables | Install new floors to portable classrooms | Complete
GAC | 142171 | HVAC - Roofing | Repair damaged of (8) HVAC equipment on roof due to hail storm. | Complete
SRE | 146535 | Playground | Install woodchips and borders. | Complete
STMS | 138255 | Gym | Acquire and install scoring table | Complete
PPD | 128463 | Shops | Establish welding/small engine shop behind Auto Shop. | Complete
District Wide | 145632 | District Wide | Repair all deficiencies found in Fire Sprinkler 2015 inspections. | Complete
STHS | 145710 | Landscaping | Install raised planters | Complete
AVEC | 147971 | Portable Relocation | Move (3) Double Portables from DT to Alta Vista Early College | Complete
GHS | 146847 | Running Track | Perform deep cleaning of artificial turf and repair to running track and | Complete
re-stripe.
CHS | 146844 | Running Track | Perform deep cleaning of artificial turf and repair of running track. | Complete
STHS | 146848 | Running Track | Perform deep cleaning of artificial turf and repair of running track. | Complete
STMS | 141421 | Kitchen Exit | Repair sidewalks/install dumpster pad. | Complete
GHS | 147722 | Field | Install sidewalk ramps behind bleachers. | Complete
PPD | 149883 | Auto Shop | Build storage and computer area. | Complete
CHS | 145600 | Gym | Repair broken seats. | Complete
CMS | 154092 | Bus Turnaround | Resurface and restripe parking. | Complete
AVECHS | 143208 | Roof | Re-roof library building | Complete
GHS | 153579 | Boys Gym | Paint exterior building | Complete

## 14-15
CMS | 117085 | PE Locker Replacement |  | Complete
GAC | 113757 | IT Office | Asbestos Abatement | Complete
GMS | 117084 | C-Wing | Asbestos Abatement | Complete
GMS | 112149 | Gym | Installation of new boiler | Complete
GMS | 117147 | PE Dressing Rooms | Replacement of lockers in Boy & Girls | Complete
MQ | 111219 | Septic Tank | Demolish and remove abandoned septic tank and pumps. | Complete
CHS | 116042 | Amphitheater | Remove and replace a section of concrete that is lifting. | Complete
CHS | 119228 | Running Track | Repair worn rubberized surface, apply 2 coats to running track | Complete
and stripe running track.
GHS | 116990 | Boys Baseball Field | Remove grass from diamond and replace with sod. | Complete
GMS | 108222 | Front Campus | Remove mulberry trees from planters and prep for planting. | Complete
GMS/C-Wing | 117895 | Athletic Dept. | New Tuff Shed | Complete
PPD | 117144 | Auto Shop | New 20' x 36 x 6" concrete pad | Complete
STE | 112234 | Bus Turnaround | Metal canopy shades for students | Complete
CHS | 93777 | Soccer Field | Install canopy shades | Complete
DT | 122898 | Portable 412 | Remodel restroom | Complete
CH-Pre-K | 117023 | Playground | New cinder block barrier to separate sandbox from wood chips. | Complete
AVECHS | 128141 | Leadership | As per Meeting - a student fell on uneven sidewalk, please repair. | Completed - February 2015
CHS | 123156 | Front Windows | Repair concrete around (6) windows due to water seeping | Complete - Jan 2015
in glass and frame.
DT | 122915 |  | Purchase Tuff Shed for storage | Complete - Jan 2015
GMS | 116703 | Baseball Field | (2) Batting Cages | Complete - Jan 2015
STHS | 124793 | Baseball Field | (4) Batting Cages | Complete - Jan 2015
GMS | 125856 | Baseball Field | New Scoreboard | Completed 2/9/15
LL | 122752 | Portable 1A & 1B | Remodel of restroom /storage room for washer and dryer, redo floor, | Project complete March 25, 2015
| 122754 |  | paint interior and exterior.
122796
122774
122799
126362
122798
128395
122914
CHS | 116932 | Softball Field | Batting cages for Softball Field | Complete
GHS | 125861 | Softball Field | Batting cages for Softball Field | Complete
GAC - Prek | 127302 | Kitchen - Serving Area | Build a counter with sink and wall cabinets. | Complete
NV | 113536 | Playground | Remove sand and fill in with wood chips. | Complete

## 13-14 Completed Projects
AE-Pre-K | 99575 | Threat Assessment | Installation of new fencing | Completed 5/30/13
CHM | 100728 | Football | Installation of new scoreboard | Completed 7/8/13
MQ | 85440 | Multi-Purpose Room | VCT Floor covering to be replaced with new. | Completed 6/27/13
MQ | 99968 | Room 107 | Abate asbestos vct - install new vct | Completed
PPD | 99749 | Roof Repairs | Auto Shop, PPD and SNP Warehouse | Completed
DT | 103357 | Portable | Relocate fence. | Complete 8/9/13
GMS | 101816 | Vocational Bldg | Abate asbestos vct - install new vct | Completed abatement
Completed VCT 7/15/13
GAC | 99743 | Electrician/Plumber | Purchase of new Morgan Building | Purchased 9/2013
GES | 103285 | Campus | Raise west fence 3" higher to prevent vandalism. | Completed 8/28/13
GHS/GMS |  | Wastewater Line | Renewing permit for placement of utilities in public right of way | 100% Complete
So we can obtain a work permit to repair the line suspended on
the River Crossing.
LM - Daycare | 105965 | Daycare Area | Painting and clean up of daycare rooms. | Complete
STE | 97636 | Art Room | Purchase of new Morgan Building | Complete
District Wide |  | Pre-K Centers | Build raised planters at sites. | 99576 - AE Pre-K Complete
AE, CHS
LM
GMS | 108800 | Gym | Relocate scoreboard | Complete
DT | 102469 | Portable | Portable Relocation # 39 DM from San Miguel | Portable Relocation/Utilities Complete
Flooring and Sidewalks Complete
Completed - New wood for ramps and 1 Heater
DT | 102469 | Portable | Portable Relocation # 39 DM from San Miguel | Completed - New wood for ramps and 1 Heater
CHS | 108957 | Sidewalks | Demo and replace concrete to (2) sections of sidewalks and a 10x20 | Complete
| 108963 |  | slab of concrete for Ground Morgan Bldg.
STMS | 109828 | Gym | Repair of floor buckling by locker rooms | Complete
District Wide | 104223 | Pre-K Centers | Build raised planters at sites. | 104223- CHS Pre-K Complete 11/27/13
AE, CHS
LM
CHS | 105901 | Gym Floor | Repair (3) entrances to gym, where floor is buckling | Complete
Northern Pre-K | 108567 | Sidewalks | Remove and pour new ADA sidewalks | Complete
108568
CHE | 112135 | Bus Pick-up | Replace 4Ft with 6FT fence | As per CMT, it was agreed fence does not need
to be replaced.
GHS | 109343 | Baseball Field | 6' Fence around boys baseball batting cages | Complete
GHS | 110437 | Baseball Field | Install new batting cages | Complete
MQ | 95182 | Playing Fields | Provide water for irrigation of playing fields. | Complete
Need to install new irrigation system.
MQ |  | Nurses Office | Install additional double doors in office. | Complete
CH-Pre-K | 117087 | Playground | Replace sand with Engineered Wood Fiber | Complete
Fall Area
STMS | 111739 | Fire Hydrants | Replacement of (5) Fire Hydrants | Complete
DP | 117024 | Sanchez Portable | Install sink, counter and water heater for science lab. | Will be completed by Const
Early College |  |  |  | Dept.
GMS | 110835 | Permit | Acquire "Right of Use Permit" for 40ft of left bank of Anthony Drain | Complete
for parking access, fence and landscaping.

## 12-13 Completed Projects
DT | 86324 | Portable Relocation | Relocate Portable # 92 DM from Chap Mid | Relocation of unit complete on 5/9/12
Utility connection in progress - Complete
LL | 86323 | Portable Relocation | Relocate Portables # 2DW and 80DW from San Miguel Elem to LL. | Complete
CHE | 90921 | Nurses Room | Abate asbestos containing floor mastic and retile. | Complete
CHS | 88266 | North Parking Lot | Repair buckled sidewalk | Complete
CHM | 90894 | Outside Water Fountain | Lay concrete, provide domestic water and electrical . | Complete
90897
90898
District Gyms |  | Gyms | Re-finish all district Gyms not including GHS Boys & Girls Gym. | Complete
VE |  | Dumpsters | Pour concrete slabs | No Action Taken 10/15/2012
AE | 90832 | Provide sidewalks | connecting to existing and landing concrete pad | Complete
to meet ADA requirements.
GAC | 83845 | Main Entrance | Install new iron gates | Complete
DT | 92316 | Need Fence between | front and back of school | Complete
GMS | 92521 | Gym | Need metal cages to separate storage. | Completed 10/31/12
PPD | 74236 | Barracks | Install fencing for furniture control. | Completed 11/19/12
DP | 91169 | Portable 32DW | Provide electrical, water and sewer and install evaporative a/c unit. | Complete
91170
91171
| 94720 |  | Need to redeck portable when abatement is complete. | Completed Abatement - Pending Floor and Tile
DP | 94720 | Portable 32DW | Need to redeck portable when abatement is complete. | Complete
DP | 97404 |  | Removal and concrete cutting. | Complete
DT | 94686 | Sanchez Portable | Concrete around portable and surrounding area. | Complete
STHS |  | New Laser Machine | Install power and vent . | Complete
District Wide | 97928 | Office | Installation of door bells as per Threat Assessment. | Complete
Elementary | 97929 |  |  | DV,LL,LU,NV,RS,STE,SP,VE and Pre-K's
Schools | 97936
97935
97756
97930
98442
97938
97931
97932
97933
District Wide | 97758 | Office | Installation of door bells as per Threat Assessment. | Complete
Elementary | 97759 |  |  | DV,LL,LU,NV,RS,STE,SP,VE and Pre-K's
Schools | 97939
97937
97934
98655
98656
98700
98652
RS | 97414 | Grounds | Need to remove shrubs (safety) | Complete
GHS | 50365 | Leadership Project | Requested by Mr. Grace on behalf of the Facilities Goal Team for the | Completed - Spring Break
Entire Campus-Metal doors, rails, poles need to be painted maroon.
District Wide | 96027 |  |  | STHS - Complete
CHS, GHS, STHS | 96543 |  |  | GHS - Complete
96526
AE-Pre-K | 100051 | ADA | Pour new sidewalk | Completed 5/7/13
DT | 100536 | Threat Assessment | Installation of new fencing w/gates | Completed 5/14/13
GHS | 99864 | Soccer Field | Demo and removal of existing concrete and pour new concrete | Completed 4/17/13
w/ADA requirements along w/new sidewalk
RS | 93203 | Mobile Home Space | New fence will be installed in this area to store equipment | Completed 4/19/13
(i.e. Tractor, District Vehicle and Lawnmower)
District Wide | 96024 | Baseball/Softball Fields | Purchase and Installation of new scoreboards. | CHS - Complete 4/16/13
CHS,STHS | 96016 |  |  | CHS - Complete 4/17/13
GHS
GHS | 101134 | Soccer Field | Double gates for new ADA sidewalk | Complete 5/30/13
LU |  | Classrooms | Painting classrooms as contractors finish remodeling | Complete

## 11-12 Completed Projects
GHS | 68457 | Leadership Project | Purchase and install new marquee. | As per R. Gallegos he will provide one
in the next Construction Phase.
STHS | 73071 | Leadership Project | Purchase and install new marquee. | Asp R. Gallegos he installed one with the
paving project.
San Miguel | 74386 | Repair all domestic | and mechanical water lines that froze due to Winter Storm 2011 | Domestic is complete, Pending mechanical
This project will be completed by Construction Dept. Summer 2012
LU |  | Playing Fields | Provide water for irrigation of playing fields. | 100% Complete
CHS | 67120 | Leadership Project | GYM - Need to re-stripe and refinish floor. | Complete 7/14/11
GHS | 40695 | Leadership Project | Girls Gym - Need to check heating and control dampers in gym. | Completed 7/6/11 - Coils are ok will change filters
in the winter.
GMS | 68436 | Leadership Project | Purchase new football scoreboard and install (Leadership Council | Completed on 5/24/11
GMS | 68432 | Leadership Project | Entire Campus around and in between all buildings level all ruts | Completed on 5/25/11
and bumps - backfill against sidewalks, clean out all storm drains.
STMS | 65036 | Leadership Project | Need electrical outlets for new CPU Lab in room 19 | Completed on 3/24/11
STMS | 68427 | Leadership Project | Repaint Flashing/cap on parapet wall both North & South buildings. | Completed on 7/14/11
STMS | 71952 | Leadership Project | North/South Bldgs - Need to abate (asbestos) in various areas then | Completed areas in North Bldg where there is
|  |  | re-tile. | no asbestos.
SM | 75469 | Asbestos Abatement | Abate approximately 100ft of Asbestos containing insulation so we can proceed with water line repairs caused by Winter Storm in Feb. | Complete
GHS |  |  | Replace 40" of broken sidewalk - Safety Issue | Complete
STE |  | Parking Lot | Seal cracks | Complete
STHS | 75574 | Tennis Courts | Repair Cracks | Complete
GAC/AE | 78258 | Morgan Building | Relocate 12' x 16' from GAC to AE - SPED Bldg | Complete
STMS |  | Fencing | New fencing on entrance of South Gate and Portables on Northend. | Complete
Purchasing | 77261 | Extend the concrete slab outside both garage door in the purchasing warehouse. |  | Complete
Warehouse
CHS | 80270 | New Laser Machine | Install power and vent .
Complete
CHS | 82084 | Gym | Straps and cables for basketball goals are in the way when shooting. | Complete
Need to relocate safety straps and cables on both courts
GAC-Pre-K | 83058 | Pre-K Classrooms | Replace counter tops with new ones to include fixtures. | Complete
GHS | 56579 | Leadership Project | Please plan for this summer to paint all frames and seal | Complete
all doors in the North Bldg, to include caulking of the new doors.
GHS | 78153 | Running Track | Rubberized surface needs to be repaired and repainted. | Complete
Track repairs are complete, Polyurethane application will be
postponed until late March due to cold weather.
GMS | 68430 | Leadership Project | Paint mascot on Gym floor | Complete
MQ |  | Original Building | Abate asbestos containing floor covering (VCT) and install new | Complete
VCT.
STHS | 78155 | Running Track | Rubberized surface needs to be repaired and repainted. | Complete
Track repairs are complete, Polyurethane application will be
postponed until late Feb or March due to cold weather.
Several Locations | 78663 | Chaparral HS - Field House, Gadsden ES, Gadsden HS (Admin, Library, V-Gym) and |  | Complete
| 78664 | STHS - Gym Equipment Data Collection Inventory and Data for use in setting up
| 78665 | Preventive Maintenance Program on equipment.
78666