## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
AVECHS | 172806 | AVEHS Annex | Upgrade electrical at AVEHS Annex | Completed 8/1/17
STE | 176228 | Playground | Create ADA Entrance for access to swings. | Completed 8/2/17
STHS | 170979 | Track | Annual Maintenance and Repair of Football Field and Track. | Completed 8/4/17
GHS | 170975 | Football Field Turf | Replace artificial turf. | 2017-08-30
STHS | 173816 | Gym | Service and repair bleachers | 2017-08-30
STHS | 176232 | Storage Lofts | Repair holes in floor of storage lofts and install access ladders. | 2017-08-30
(Identified by POMS)
CMS | 177897 | Lobby/Admin | Paint | 2017-08-30
STHS | 176333 | 200-300 Restrooms | Replace partitions. | 2017-08-30
YH | 167093 | North Wing | Install portable building | 2017-08-31
STHS | 174522 | Playfields | Consult with NMSU Ag Dept. on improving playfields grass growth | 2017-08-31
CHE | 177461 | Computer Lab | Replace windows and paint building. | 2017-09-15
STHS | 176232 | Loft in Shops | Replace floors and access ladders. | 2017-09-15
SPE | 176081 | Playground | Curbs and Woodchips | 2017-09-15
GAC | 170964 | Server Room | Upgrade A/C system. | 2017-09-15
VE | 175577 | Hydronic | Treat water. | 2017-09-30
GMS | 178849 | Hydronic | Treat water | 2017-09-30
STHS | 174354 | Fields/Grounds | Concrete anchoring | 2017-09-30
District Wide | 174521 | Lighting Controls | Implement Trane Tracer ES Lighting Controls scheduling lighting | 2017-09-15
energy savings.
STHS | 176764 | Science Labs | Replace Acid Dilution tank for proper disposal of acid to | 2017-09-15
eliminate odors.
STHS | 174354 | Softball Field | Create concrete slabs to anchor bleachers and control erosion. | 2017-09-30
CHS | 176086 | Grounds | Repair pump for irrigation system. | 2017-09-30
GHS | 170976 | Track | Annual Maintenance of Track. | 2017-10-06
District Wide | 174520 | Kitchen Energy | Monitor Kitchens energy use including HVAC to be able to breakout | 2017-11-15
costs for SNP Dept.
YH | 167094 | Playground | Install curbs to contain wood-chips | On hold until latter part of Fiscal Year 17-18