## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
GAC | 182808 | Superintendent Office | Remodel and painting of offices | Completed 10/20/17
| 182809 | Superintendent Office | Installation of carpet | Completed 10/20/17
District Wide | 174521 | Lighting Controls | Implement Trane Tracer ES Lighting Controls scheduling lighting | Completed 10/25/17
energy savings.
YH | 167093 | North Wing | Install portable building | Completed 10/25/17
GAC | 170964 | Server Room | Upgrade A/C system. | Completed 10/25/17
STM | 180181 | Office Area | Repair sidewalk and seal building to stop water from entering | Completed 10/25/17
building at office area.
STHS | 176964 | Science Labs | Replace Acid Dilution tank for proper disposal of acid to | Completed 10/25/17
eliminate odors.
YH | 180201 | Entrance Gate | Create ADA walk-in entrance by street. | Completed 10/25/17
VE | 181590 | Bus Turnaround | Repair bus turnaround where trash truck loads | Completed 10/25/17
LL | 180887 | Bus Turnaround | Installed fence between playground and bus turnaround. | Completed 10/25/17
CMS | 181589 | Cafeteria | Paint Cafeteria and stage | Completed 10/25/17
STE | 184185 | Hydronic System | Treat water | Completed 10/31/17
STHS | 173816 | Gym | Service and repair bleachers | 2017-10-31
GAC | 180974 | Riser | Make repairs and corrections to FDC | 2017-11-15
STHS | 180973 | Science Room | Upgrade counter-tops and casework. | 2017-11-30
SPE | 181592 | Above Kitchen | Build cages to keep pigeons out of mechanical area | 2017-11-30
CHS | 177490 | Kitchen | Boiler for the Kitchen needs to be replaced | 2017-11-30
RS | 181528 | Entrance | Create a more secure entrance. | 2017-11-30
STH | 176333 | Restrooms | Replace restroom partitions in 200 and 300 hallway bathrooms. | 2017-11-30
GE | 184187 | Multi-Purpose | Install blinds on windows | 2017-12-20
District Wide | 174520 | Kitchen Energy | Monitor Kitchens energy use including HVAC to be able to breakout | 2017-12-20
costs for SNP Dept.
SNP Complex | 178168 | SNP Offices | Renovate and remodel old ADVEC for SNP Dept. | 2017-12-20
CHS | 179169 | Dugouts | Enclose dugouts | 2017-12-20
CMS | 181529 | Parent Drop-off | Create Parent-Drop Off. | 2018-01-31
VE | 181530 | Hydronic System | Repair of Hydronic System | 2018-06-30